## To-Do List
Simple task List
TASK | STATUS | PRIORITY | STORY POINTS | DUE DATE | DELIVERABLE | STATUS KEY | PRIORITY KEY
Set up github for wordle application | Done | High | 1 |  | Repository is up and running | To Do | High
Write test case for word selector | To Do | High | 1 | 2023-09-12 | Review test case | In Progress | Medium
Develop function to select random word | To Do | Medium | 2 | 2023-09-12 | Passes test cases | Done | Low
Write the gameplay loop logic (repeat for MAX_TRIES valid attempts) | To Do | Medium | 2 | 2023-09-12 | Passes test cases | On Hold
Write test cases for input validation (ensure guess is in VALID_WORDS) | To Do | High | 1 | 2023-09-12 | Review test case | Cancelled
Write input validation (ensure guess is in VALID_WORDS) | To Do | Medium | 2 | 2023-09-13 | Passes test cases
Write test cases for scoring algorithm | To Do | High | 1 | 2023-09-12 | Review test cases
Write scoring algorithm | To Do | High | 4 | 2023-09-20 | Passes test cases
Review MVP with Client | To Do | Medium | 1 | 2023-09-20 | Review with client
Review with senior dev | To Do | Medium | 1 | 2023-09-20 | Review with senior dev
Write documentation (rough draft) | To Do | Low | 1 | 2023-09-12 | readme.md headers
Write documentation (finished product) | To Do | Low | 1 | 2023-09-20 | Fill out all headers for readme.md
Note on E2: Story points An estimate of the relative complexity of a task. If we say task a is 1 story point and task b is 2 story points we mean we believe task b is twice the size of a for us. We typically rate using a Fibonacci sequence to reflect the fact that as tasks grow our ability to estimate becomes less precise: 1, 2, 3, 5, 8, 13, 21, 34, 55, 89

## Alternative platforms
Github | Link | Highlights
Recommended |  |  | All software development projects of a significant size use some form of task management
|  | New project management view! | Task manamgent helps us:
| https://github.com/features/issues | Dev focused | Prioritise
|  | Simple | Coordinate
|  | Free | Communicate
Trello
Today's software development tools focus on keeping task management close to the programs themselves, integrating with version control and other tools.
|  | Established | Simple workflows are increasingly preferred
| https://trello.com/home | Easy to use | Hosting (SaaS) is becoming more popular
|  | Lots of dev friendly integrations | Most popular services offer free entry-level plans
Free limited use
Australian owned
JIRA
Very mature
| https://www.atlassian.com/software/jira | Powerful workflows
Industry-standard for much of the last 15 years
Complex
Australian owned and made
meistertask
Growing in popularity
| https://www.meistertask.com/ | Versatile
Scales
Other notables
Wrike
Asana
todoist
Any.do
Monday.com
Many, many more!
SOFTWARE INDUSTRY TOOLS