## To-Do List
Simple task List
TASK	STATUS	PRIORITY	STORY POINTS	DUE DATE	DELIVERABLE		STATUS / KEY		PRIORITY / KEY
Set up github for wordle application	Done	High	1		Repository is up and running		To Do		High
Write test case for word selector	Done	High	1	09/12/2023	Review test case		In Progress		Medium
Develop function to select random word	To Do	Medium	2	09/20/2023	Passes test cases		Done		Low
Write the gameplay loop logic (repeat for MAX_TRIES valid attempts)	To Do	Medium	2	09/20/2023	Passes test cases		On Hold
Write test cases for input validation (ensure guess is in VALID_WORDS)	Done	High	1	09/20/2023	Review test case		Cancelled
Write input validation (ensure guess is in VALID_WORDS)	To Do	Medium	2	09/20/2023	Passes test cases
Write test cases for scoring algorithm	To Do	High	1	09/20/2023	Review test cases
Write scoring algorithm	To Do	High	4	09/22/2023	Passes test cases
Review MVP with Client	To Do	Medium	1	09/27/2023	Review with client
Review with senior dev	To Do	Medium	1	09/27/2023	Review with senior dev
Write documentation (rough draft)	Done	Low	1	09/12/2023	readme.md headers
Make a flow chart	To Do	High	1	09/20/2023	Review flow chart
Write documentation (finished product)	To Do	Low	1	09/27/2023	Fill out all headers for readme.md

## Alternative platforms
Github	Link	Highlights
Recommended					All software development projects of a significant size use some form of task management
		New project management view!			Task manamgent helps us:
	https://github.com/features/issues	Dev focused			Prioritise
		Simple			Coordinate
		Free			Communicate
Trello
					Today's software development tools focus on keeping task management close to the programs themselves, integrating with version control and other tools.
		Established			Simple workflows are increasingly preferred
	https://trello.com/home	Easy to use			Hosting (SaaS) is becoming more popular
		Lots of dev friendly integrations			Most popular services offer free entry-level plans
		Free limited use
		Australian owned

JIRA

		Very mature
	https://www.atlassian.com/software/jira	Powerful workflows
		Industry-standard for much of the last 15 years
		Complex
		Australian owned and made

meistertask

		Growing in popularity
	https://www.meistertask.com/	Versatile
		Scales

Other notables
Wrike
Asana
todoist
Any.do
Monday.com
Many, many more!